## Slide 1
2026-2027 Accounting Cost Reduction Plan
This plan aims to reduce Accounting operating cost through a combination of GBS migration and AI/Automation-led process optimization across AP/AR, GL, Collection and Invoicing.
SAVINGS POTENTIAL
$0.54M - 1.23M
Low case without GBS: $544.2K
High case with GBS: $1.12M
INVESTMENT & RETURN
$150K / 0.8 - 2.6 yrs
AI & Automation investment: $150K
ROI range: 0.8 to 2.6 years
IMPACT APPLICATION
5 + 3
Existing: PCS / VAT / AR Portal / MDM / Credit
New: Enterprise WeChat / AI / RPA
1. AP / AR
Kickoff: Apr 2026 | Existed Cost: $1,715K | Saving Target: $520K
Actions:
Total HC 34, convert the AP/AR team to the GBS model; keep 8 HC in Shanghai and move 23 HC to GBS.
Note:
$20K / HC or 50% of China Cost, 9 months transition cycle
2. Collection
Kickoff: April 2026 | Existed Cost: $1,570K | Saving Target: $314K
Actions:
Total HC 36, deliver around 20% savings through AI/Automation-enabled productivity improvement.
Note:
Detailed scope to be identified.
3. GL
Kickoff: July 2026 | Existed Cost: $1,923K | Saving Target: $219K
Actions:
Total HC 28, convert part of the GL team (14 FTE) to the GBS model after process mapping and operating-model validation.
Note:
100% band 5 and 30% band 6 move to GBS
4. Invoicing
Kickoff: April 2026 | Existed Cost: $398K | Saving Target: $70K
Actions:
Total HC 9, leverage AI/Automation to improve invoicing efficiency by about 20%.
Note:
Keeping local execution for compliance

## Slide 2
Business Current Status
Current FTE allocation by business step and legal entity, based on the latest workload snapshot.
Step | ITSC | AA | AB Service | CD Service | BJBP+CTC | HK
01 Master Data Prep | 0.27 | 0.01 | 0.02 | 0.01 | 0.01 | 0.04
02 Invoicing Support Delivery | 10.50 | 0.09 | 0.22 | 0.07 | 0.02 | 0.12
03 Reconciliation and Dispute | 2.66 | 0.21 | 0.52 | 0.63 | 0.09 | 0.21
04 Collection and Commitment | 10.60 | 0.57 | 1.08 | 1.10 | 0.13 | 0.72
05 Cash Application | 2.22 | 0.19 | 0.13 | 0.19 | 0.09 | 0.07
06 Notes or Special Receipts | 0.00 | 0.00 | 0.00 | 0.01 | 0.00 | 0.14
07 Escalation and Legal | 0.11 | 0.01 | 0.01 | 0.01 | 0.01 | -
08 Write-off | 0.12 | 0.00 | 0.00 | 0.01 | 0.00 | 0.02
09 Reporting and Improvement | 0.72 | 0.01 | 0.02 | 0.03 | 0.00 | 0.02
10 Others | 0.24 | 0.00 | 0.03 | 0.07 | 0.02 | 0.00
Total FTE | 27.44 | 1.09 | 2.04 | 2.12 | 0.38 | 1.33
Total FTE
34.400
Target FTE
6.880
20% of Total FTE
FCST FTE
3.544
Under Review 3.000
Pending Approval 0.056
Approved 0.000
Pending Quote 0.488
Current identified pipeline covers part of the target, with further conversion still required.

## Slide 3
Process Footprint View
FTE Threshold
0.10
Flows below this value are hidden.
Gray: No optimization potential
Green: Click for detailed actions
Pre-Invoice
Collection
Cash App
Master Data
0.3
Special Invoice
0.4
Invoice Delivery
1.4
Dispute
1.3
Commitment
8.2
Tracking
0.7
Allocation
1.6
Data Support
0.6
Priority should stay on high-FTE flows with confirmed action linkage.

## Slide 4
Identified Improvement Points
Current change opportunities summarized from the workbook action sheet.
Focus: prioritize by maturity, FTE impact, and cost.
System / Step / Status
Type
Default Order
FTE / Cost Sort
Card View
Use Enterprise WeChat
Type: New
FTE: 1.000
Cost: -
Reduce repetitive reminder work and improve communication traceability.
Enterprise WeChat + AI
Type: AI
FTE: 2.000
Cost: -
Enable layered handling and automation through AI-backed workflow.
Credit receipt capture
Type: CR
FTE: 0.100
Cost: -
Pull bank receipt data into Credit and reduce manual collection effort.
Payment habit field
Type: CR
FTE: 0.010
Cost: -
Add customer payment behavior field for quicker review and analysis.
Structured follow-up format
Type: CR
FTE: 0.090
Cost: -
Standardize collection records to reduce duplicate clarification.
Invoice line sequence
Type: CR
FTE: 0.020
Cost: CNY 100,000
Adjust line-item sequence in invoice systems after business approval.